## Schedules
PROJECT: GED Evaluation & Accompagnment
Mission Chief : Andre Bena Mcs, MBA, PhD.
| Performance : Evaluation report |  | Start Date | 2018-09-11 | End Date | 2018-12-21
| Completed | 18.92%
| Remainder | 81.08%
Category | Tasks | Resource | Start Date | Duration | Completed | Incompleted
Initiation | Kick-off-Meeting Phase 1 (Evaluation) | A.Bena & Team | 2018-09-10 | 1 | 1 | 0
Initiation | complete Administrative formalities | DSI | 2018-09-11 | 0 | 0 | 0
Initiation | Plan Detailled mission activities | A.Bena | 2018-09-11 | 2 | 2 | 0
Initiation | Approve & validate detailed Planing | DSI | 2018-09-13 | 0 | 0 | 0
Initiation | Sign Mission Contract | DSI & A.Bena | 2018-09-13 | 0 | 0 | 0
Requirement | Collect project documentation & Reading | A.Bena | 2018-09-13 | 1 | 1 | 0
Requirement | Review functional business requirements | A.Bena | 2018-09-14 | 5 | 5 | 0
Requirement | Review application architecture requirements | A.Bena | 2018-09-21 | 3 | 3 | 0
Requirement | Review technical architecture requirement | A.Bena | 2018-09-26 | 2 | 1 | 1
Requirement | Review project logistics requirements | A.Bena | 2018-09-28 | 1 | 1 | 0
Specification | Technical achitecture review | A. Bena | 2018-10-01 | 2 | 0 | 2
Specification | Application architectur review | A. Bena | 2018-10-03 | 3 | 0 | 3
Specification | Review project deliverables status | A. Bena | 2018-10-09 | 1 | 0 | 1
Specification | Code review: Programming Paterns | I. Azinyue | 2018-10-10 | 10 | 0 | 10
Specification | Code review: Programming Models | A.Bena | 2018-10-24 | 4 | 0 | 4
Specification | Data model review | M. Chegaing | 2018-10-28 | 5 | 0 | 3
Performance | Test specification | M. Chegaing | 2018-11-05 | 5 | 0 | 5
Performance | Key functional testing | Team | 2018-11-12 | 5 | 0 | 5
Performance | load Testing | Team | 2018-11-19 | 3 | 0 | 3
Performance | Tests result analysis | M. Chegaing | 2018-11-24 | 2 | 0 | 2
Methodology | review GED project documentation process | A. Bena | 2018-11-26 | 2 | 0 | 2
Methodology | review GED development cycle | A. Bena | 2018-11-28 | 2 | 0 | 2
Methodology | review incident management process | A. Bena | 2018-12-02 | 2 | 0 | 2
Methodology | review change management process | A. Bena | 2018-12-04 | 2 | 0 | 2
Methodology | review release management process | A. Bena | 2018-12-07 | 2 | 0 | 2
Documentation | write mission report | A. Bena | 2018-12-11 | 6 | 0 | 6
Documentation | Deliver Drafted Mission report | A. Bena | 2018-12-19 | 0 | 0 | 0
Documentation | review mission report & Prepare next Phase 2 | DSI & A.Bena | 2018-12-19 | 3 | 0 | 3
Present Results | Deliver Final Mission report & briefing | A. Bena | 2018-12-21 | 0 | 0 | 0
| Kick-off-Meeting Phase 2 (accompagnment) | A. Bena & Team | 2018-12-22 | 0 | 0 | 0